## Slide 1: PERT Chart

## Slide 2: PERT Chart
Stands for Program Evaluation and Review Technique.
A PERT chart is a project management tool that provides a graphical representation of a project's timeline.
The Program Evaluation Review Technique (PERT) breaks down the individual tasks of a project for analysis.
PERT charts are considered preferable to Gantt charts because they identify task dependencies.
PERT Chart is difficult to interpret.

## Slide 3: Components of PERT Chart
Event or Milestone are the specific accomplishments in a project and represented using numbered circle or rectangle.
Activities are the time consuming aspects of the project. Represented using arrows.
Critical Path is the sequence of events in a project that requires most / maximum time to complete.

## Slide 4: Components of PERT Chart: Tasks
Dependent Task represented using dotted line do not require resources.
Dependent Task represented using arrows require resources.
Concurrent Task
Dummy Task

## Slide 5: Components of PERT Chart
1
2
3
System Design
10
Arrange Hardware
5
4
5
Programming
20
Installation
5
8
10
7
9
6
11
Machine Code
5
Code Testing
10
Documentation
(Manual)
5
System Testing
15
Training
5
User Acceptance Test
5
Implementation
5

## Slide 6: Working of PERT Chart
A PERT chart helps a project manager analyze a project's tasks and estimate the amount of time required to complete each task in the project.
Using this information, the project manager can estimate the minimum amount of time required to complete the entire project.
This information also helps the manager develop a project budget and determine the resources needed to accomplish the project.
A PERT chart uses circles or rectangles called nodes to represent project events or milestones.

## Slide 7: Working of PERT Chart …
These nodes are linked by vectors or lines that represent various tasks.
Dependent tasks are items that must be performed in a specific manner.
For example, if an arrow is drawn from Task1 to Task 2 on a PERT chart, Task 1 must be completed before work on Task 2 begins.
Items at the same stage of production but on different task lines within a project are referred to as parallel tasks. They're independent of each other, but they're planned to occur at the same time.